## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Karthik | Mar 02 | LLM not responding due to API misconfiguration | Sprint 1 | Sharanya | Functional | Fixed API key issue | Mar 03 | Closed | Resolved after config fix
2 | Karthik | Mar 05 | Incorrect prompt output formatting | Sprint 1 | Sharanya | UI/Logic | Improved prompt templates | Mar 06 | Closed | Formatting corrected
3 | Karthik | Mar 12 | Calculator tool returning wrong values | Sprint 2 | Sharanya | Functional | Fixed calculation logic | Mar 13 | Closed | Tested successfully
4 | Karthik | Mar 13 | Weather API mock failing randomly | Sprint 2 | Sharanya | API | Added error handling | Mar 14 | Closed | Stable now
5 | Karthik | Mar 15 | Agent not invoking tools correctly | Sprint 2 | Sharanya | Integration | Updated prompt instructions | Mar 16 | Closed | Tool usage fixed
6 | Karthik | Mar 22 | Agents not sharing context properly | Sprint 3 | Sharanya | Functional | Implemented shared memory | Mar 23 | Closed | Working fine
7 | Karthik | Mar 23 | Memory not persisting across sessions | Sprint 3 | Sharanya | Data | Fixed memory config | Mar 24 | Closed | Persistence achieved
8 | Karthik | Mar 25 | Agent communication delay | Sprint 3 | Sharanya | Performance | Optimized chaining logic | Mar 26 | Closed | Improved speed
9 | Karthik | Apr 01 | API endpoint failing intermittently | Sprint 4 | Sharanya | API | Fixed routing issue | Apr 01 | Closed | Stable endpoints
10 | Karthik | Apr 02 | Frontend not receiving API response | Sprint 4 | Sharanya | Integration | Fixed CORS issue | Apr 02 | Closed | Frontend-backend synced

## Sheet2
Logical
User Interface
Maintainability
Standards
Others